## Sheet1
Order # | Title | Application Date | Order Date | Asset | Outcome
P.U.12(2026) | Application by Newfoundland and Labrador Hydro for approval of capital expenditures for the life extension of Unit 7 at the Bay d’Espoir Hydroelectric Generating Facility, pursuant to section 41 of the Act. | 2025-06-20 | 2026-04-21 | Unit 7 | 1. Capital expenditures in an amount of up to $66,265,000 for the life extension of Unit 7 at the Bay d’Espoir Hydroelectric Generating Facility are approved. 2. Hydro shall provide updates on the execution of the Unit 7 life extension project in accordance with the subsequent directions of the Board.
Significant Elements of Timeline: | Date | Description
Application | 2025-06-20 | Bay d'Espoir Unit 7 - commissioned in 1977; 154 MW generation capacity: - multi-year capital investment to ensure continued safe, reliable and efficient operation for at least 25 years; - work requires complete disassembly of Unit 7; - project execution expected to take 4 years; and, - requests approval of $85.3M capital budget to complete the project
Request for Additional Information from PUB | 2025-08-08 | NL Hydro identified three alternatives (Deferral, Like-for-Like refurbishment/replacement, and Cluster life extension with additional required work. PUB seeks analysis of a fourth alternative: the uprate of Unit 7 (analysis to include cost estimates, quantification of increased capacity on Bay d'Espoir hydrology, comparison of efficiency over status quo).
Intervenor Submissions | 2025-09-12 | Island Industrial Customers Group (IC) and Newfoundland Power (NP) give notice they will participate as intervenors in the application.
Additional information from NLH | 2025-09-23 | NL Hydro provides report answering request put to them by the PUB.
Request for Clarification from PUB | 2025-10-06 | PUB seeks clarifications in relation to the response filed.
Additional information from NLH | 2025-10-16 | NL Hydro responds to request put to them by the PUB.
Schedule | 2025-10-20 | PUB issues review schedule for the application.
RFIs filed | 2025-10-30 | RFIs from NP to NL Hydro and from the PUB to NL Hydro received.
Correspondence to Parties | 2025-11-06 | PUB grants extension for deadline to file responses to RFIs.
Responses to RFIs filed | 2025-11-14 | NL Hydro responses to all RFIs filed.
Coomments from Parties | 2026-03-13 | Comments from NL, IC and the Consumer Advocate received.
Reply from NL Hydro | 2026-03-18 | NL Hydro's response to comments filed.
Approval granted. | 2026-04-21 | PUB issues P.U.12(2026) as described above.